## Gantt
Loftus frukt og saft
|  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
| Who is responsible? | External contact?
LFoS new website
Insights/analysis/design foundation | bar: Week 1 to Week 3
Define purpose of site | All | Product owner/ Client CEO | bar: Week 1
Insights/analysis | Karoline/Daniel | Product owner assistance in working out questions for insight | bar: Week 1
Strategy/development workshop | Henrik | Determine target audience/scope | bar: Week 1
User insights | Karoline/Daniel | bar: Week 2
Design workshop (moodboard etc) | Henrik | Include product owner and other interested parties | bar: Week 2
Style tile development | Daniel/Ina | Product owner needs to sign off | bar: Week 3
Wireframing | Daniel | bar: Week 3
Cross team kick off | Henrik
Content | bar: Week 2 to Week 4
Design process | Daniel/Karoline | bar: Week 2 to Week 4
Write copy | Ina | bar: Week 3 to Week 4
Acquire images | Ina | bar: Week 3 to Week 4
Design sprint | Henrik | bar: Week 4
Weekly Kanban meetings | Henrik | Product owner | bar: Week 5 to Loftus frukt og saft Week 12
Development | bar: Week 5 to Loftus frukt og saft Week 12
Coding | Umran/ | bar: Week 5 to Loftus frukt og saft Week 10
QA | Henrik | bar: Loftus frukt og saft Week 7 to Loftus frukt og saft Week 11
Accessibility | Henrik | bar: Loftus frukt og saft Week 7 to Loftus frukt og saft Week 11
User testing | Karoline | bar: Loftus frukt og saft Week 8; Loftus frukt og saft Week 10; Loftus frukt og saft Week 12
Review | bar: Loftus frukt og saft Week 13
Review site | Henrik | Product owner/CEO | bar: Loftus frukt og saft Week 13
Implement final changes | Henrik/Umran | bar: Loftus frukt og saft Week 13
Sign off final site/handoff | Henrik | Product owner/CEO
Projected working hours/cost | [15 empty] | Total projected manhours | Hourly wage | Total projected cost for workers
Henrik |  |  | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 487.5 | 560 | 273000
Karoline |  |  | Week 1: 37.5; Week 2: 37.5; Week 3: 37.5; Week 4: 37.5; Loftus frukt og saft Week 8: 37.5; Loftus frukt og saft Week 10: 37.5; Loftus frukt og saft Week 12: 37.5 | 262.5 | 560 | 147000
Daniel |  |  | Week 1: 37.5; Week 2: 37.5; Week 3: 37.5 | 112.5 | 560 | 63000
Ina |  |  | Week 1: 37.5; Week 3: 37.5; Week 4: 37.5 | 112.5 | 560 | 63000
Umran |  |  | 37.5 |  |  |  | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 375 | 1300 | 487500
Total |  |  | 187.5 | 112.5 | 300 | 112.5 | 75 | 75 | 75 | 112.5 | 75 | 112.5 | 75 | 112.5 | 75 | 1350 |  | 1033500

## Team
TEAM
Henrik Project manager
Karoline Konseptutvikler/Designer
Fredrik Frontend
Umran Utvikler
Ina Innholdsutvikler
External
Peter Product Owner
Charles CEO